## design
# | Axis | What varies | Objects | Methods | Runs | Primary metrics | Status | Artefacts
A | Method x object | 4 reconstruction methods on a fixed object set | 6 (bus shelter, bench, bollard, lamppost, bus-stop sign, information sign) | COLMAP (SIFT), hloc+COLMAP (SuperPoint+LightGlue), MASt3R-GA, VGGT | 24 | accuracy/completeness median (cm), accuracy@3cm, completeness@3cm, F1@3cm, M3C2, density uniformity (CV of NN distance) | Complete | summary_all_objects_accuracy_f1_EN.xlsx, 6 per-object mini-reports, site/*.html
B | Capture protocol | T1 close-ups + orbit / T2 overhead only / T3 full orbit only, image count held constant | 2 (bollard, information sign) | COLMAP, MASt3R-GA | 12 (exp_081-092) | F1@3cm with 95% block-bootstrap CI (2000 draws, 5 cm blocks), pairwise dF1 + CI, registration rate | Complete | capture_comparison_summary.xlsx, capture_comparison_sensitivity.json, site/capture_comparison.html
C | Image count | Nested subsets: 15/30/45/60 and 25/50/75/100 images, greedy farthest-point coverage selection | 2 (bollard, information sign) | COLMAP, MASt3R-GA | 16 (exp_093-108) | same as A, as a function of n | Reconstructions done; LiDAR registration + metrics not started | outputs/experiments/exp_093-108/*.ply, timings in experiment_metrics.jsonl
D | Computational cost | - (measured on every run of B and C) | 4 | COLMAP, MASt3R-GA | 28 logged runs | total + per-stage wall time, peak RAM, peak VRAM, dense point count, mean reprojection error, mean track length; git commit, library versions, hardware | Data captured; no summary table yet | docs/tables/experiment_metrics.jsonl
E | Capture modality | Photo (individually-shot HEIC) vs video walk-around | to be fixed | to be fixed | 0 processed | same as A + acquisition time, frames per minute | New video captured, unprocessed; legacy video corpus available | -